## Sheet1
Bug ID | Bug Title | Module | Expected Behavior | Actual Behavior | Severity | Reporter | Submit Date
BUG-01 | Post edit loses formatting | Posts | Should retain formatting | Text becomes plain | Medium | Rifat Sarwar | 2024-10-01
BUG-02 | Create Post page missing media upload | Posts | Media upload option is missing in post creation. | Only text can be entered | Medium | Ahmed Shafin Ruhan | 2024-10-10
BUG-03 | Infinite scroll loads duplicates | Posts | New posts only | Same posts repeat | Medium | Tahsin Bin Reza | 2024-10-13
BUG-04 | Blocked users can still message | Chat | Messaging should be disabled | Blocked user sends messages | High | Ahmed Shafin Ruhan | 2024-10-17
BUG-05 | Profile picture not updating | User Profile | Should change on upload | Old image remains | Medium | Ahmed Shafin Ruhan | 2024-10-28
BUG-06 | Post timestamps incorrect | Posts | Should show correct time | Future timestamps shown | Medium | MD. Nazmus Sadiq | 2024-11-09
BUG-07 | Follower count not displayed | User Profile | Profile should show followers/following | Follower count section missing | Low | Rifat Sarwar | 2024-11-24
BUG-08 | Event registration not working | Events | User should be able to register for an event | Clicking register does nothing | High | MD. Nazmus Sadiq | 2024-12-03
BUG-09 | Search ignores posts | Search | Search should include posts | Only user profiles shown | Medium | Rifat Sarwar | 2024-12-09
BUG-10 | Admin panel missing moderation tools | Admin Panel | Should have ban/edit options | No actions visible | High | Ahmed Shafin Ruhan | 2024-12-14
BUG-11 | No password validation on signup | Authentication | Passwords should meet criteria | Weak passwords accepted | High | Tahsin Bin Reza | 2024-12-17
BUG-12 | Irrelevant news scraped | Posts | Only relevant news should be scraped | Unnecessary news are also scraped | High | MD. Nazmus Sadiq | 2024-12-18
BUG-13 | Chat not loading on mobile | Chat | Chat should work on mobile | Chat area is blank | Critical | Tahsin Bin Reza | 2024-12-21
BUG-14 | Chat messages not scrolling to latest | Chat | Should scroll to newest | Stuck at top | Low | Adib Ahmed | 2024-12-22
BUG-15 | User bio not saving | User Profile | Bio should save | Disappears after refresh | Medium | MD. Nazmus Sadiq | 2025-01-10
BUG-16 | Irregular tab size | Posts | Tabs should have same size | Diferent tab size based on content | Medium | Adib Ahmed | 2025-01-17
BUG-17 | Dark mode doesn't apply to modal windows | UI | Should be consistent | Light modal on dark theme | Low | Rifat Sarwar | 2025-01-20
BUG-18 | Notifications load slowly | Notifications | Should be instant | Takes several seconds | Medium | Tahsin Bin Reza | 2025-01-26
BUG-19 | Like button doesn't toggle | Posts | Like should toggle | Click does nothing | Medium | Tahsin Bin Reza | 2025-02-06
BUG-20 | Twitter scraping out of order | Posts | Twitter posts should be sorted based on date | No sorting of news | Medium | MD. Nazmus Sadiq | 2025-02-17
BUG-21 | Unfollow button not visible | User Profile | Should toggle after follow | Still shows follow | Low | Ahmed Shafin Ruhan | 2025-02-25
BUG-22 | Event images not loading | Events | Event posters should be visible | Broken image icon | Low | Tahsin Bin Reza | 2025-03-01
BUG-23 | Multiple login sessions allowed | Authentication | Should restrict sessions | Same user logged in multiple devices | Low | Ahmed Shafin Ruhan | 2025-03-04
BUG-24 | Password reset email not sent | Authentication | Email should be sent | No email received | High | Rifat Sarwar | 2025-03-06
BUG-25 | Post comment count not updating | Posts | Count should increase | Static number shown | Medium | MD. Nazmus Sadiq | 2025-03-08
BUG-26 | Search results not clickable | Search | Should open result | Clicking result does nothing | Medium | Rifat Sarwar | 2025-03-09
BUG-27 | Event calendar UI broken in Firefox | Events | Should render correctly | Layout distorted | Low | Tahsin Bin Reza | 2025-03-10